## timeline overview
Tasks | Frequency | Due Date
Start date: July 1, 2014 |  | Complete timeline will be negotiated with DBHR based on individual coalition readiness. | First Year | Ongoing | Annually | Update 2015
Getting Started
1. Register and participate in The Athena Forum | Ongoing | within 2 weeks of start
2. Select CPWI Community | --- | ---
a. Submit selection packet | First Year only | by March 31 | x
b. Issue media release | First Year only | within 60 days from DBHR approval | x
3. Community Coalition Coordinator (.5 FTE ) for each CPWI community | --- | ---
a. Review job description with DBHR | First Year & As needed | Prior to posting | x
b. Ensure Coordinator is working with coalition | Ongoing | Starting July 1 |  | x
4. Confirm SAPISP and P-I services | Annually | Within 30 days prior to start of school |  |  | x
Capacity
1. Recruit and retain membership | --- | ---
a. 8 of 12 sectors | Ongoing | Starting July 1 |  | x
b. Membership section in Strategic Plan | Ongoing & Update 2015 | [enter date] |  | x |  | x
c. Conduct ‘Coalition Assessment Tool’ (CAT) | Annually | October |  |  | x
d. Complete ‘Community Profile’ | First Year & Update 2015 | Within 45 days from approval of Plan |  | x |  | x
2. Community coalition orientation | First Year & As needed | [enter date] | x
3. Establish and maintain coalition structure | Ongoing & Update 2015 | [enter date] |  | x |  | x
4. Engage key leaders in coalition’s CPWI efforts | Annually | [enter date] |  |  | x
5. Gather community information and feedback | Ongoing | [enter date] |  | x
6. Participate in training and technical assistance | Ongoing | --- |  | x
Assessment
1. Conduct Needs Assessment | --- | ---
a. Establish process for assessment | First Year & Update 2015 | [enter date] | x |  |  | x
b. Conduct Assessment | First Year & Update 2015 | [enter date] | x |  |  | x
c. Conduct ‘Community Survey’ | First Year & Annually | September-December | x |  | x
d. Prioritize outcomes and write into Strategic Plan | First Year & Update 2015 | [enter date] | x |  |  | x
2. Conduct Resources Assessment | --- | ---
a. Establish process for assessment | First Year & Update 2015 | [enter date] | x |  |  | x
b. Conduct Assessment | First Year & Update 2015 | [enter date] | x |  |  | x
c. Prioritize outcomes and write into Strategic Plan | First Year & Update 2015 | [enter date] | x |  |  | x
Planning
1. Select goals, objectives, strategies, & programs/activities
a. Coalition determines goals and objectives | First Year & Update 2015 | Update June 15, 2015 | x |  |  | x
b. Coalition determines strategies, and programs/activities | First Year &Update annually | June 15 | x |  | x
2. Develop Prevention Strategic Plan | First Year & Update 2015 | Update June 15, 2015 | x |  |  | x
3. Confirm partnerships for implementation of strategies and programs/ activities | First Year & Annually | [enter date] | x |  | x
Implementation
1. Maintain active community coalition | Ongoing | Starting July 1 |  | x
a. Coordinator support Coalition | Ongoing | Starting July 1 |  | x
b. Monthly full Coalition meetings | Ongoing | Starting July 1 |  | x
c. Review and revised as needed Coalition structure | Annually | [enter date] |  |  | x
d. Complete task in Community Coalition Guide | Ongoing | Starting July 1 |  | x
2. Participate in monthly meetings with DBHR | Ongoing | Within 30 days |  | x
a. Participate in monthly Learning community Meetings | Ongoing | Starting July 1 |  | x
b. Participate in monthly site check-in meetings | Ongoing | [enter date] |  | x
3. Implement media strategies | Ongoing | [enter date] |  | x
4. Implement strategies and programs/activities according to Strategic Plan
a. Organize and implement P-I services | Ongoing | September - June |  | x
b. Implement capacity building strategies & activities | Ongoing | [enter date] |  | x
c. Implement cultural competency strategies & activities | Ongoing | [enter date] |  | x
d. Implement sustainability strategies & activities | Ongoing | [enter date] |  | x
e. Implement public awareness campaign(s) | Ongoing | [enter date] |  | x
f. Implement environmental strategy(ies) | Ongoing | [enter date] |  | x
g. Implement selected direct prevention strategy(ies) | Ongoing | [enter date] |  | x
Reporting and Evaluation
1. Develop reporting and evaluation strategies
a. Determine coalition’s intended major outcomes, impacts | First Year & Update 2015 | [enter date] | x |  |  | x
b. Determine how evaluation information will be shared | First Year & Update 2015 | [enter date] | x |  |  | x
2. Complete PBPS reporting
a. Coalition & community organization functioning | Ongoing | [enter date] |  | x
b. ‘Coalition Assessment Tool’ (survey) | Annually | October |  | x
c. Report public awareness & environmental strategy(ies) | Ongoing | [enter date] |  | x
d. Report direct prevention strategy(ies) | Ongoing | [enter date] |  | x
3. Review and analyze output and outcome information with coalition according to Strategic Plan.
a. Use the ‘Coalition Assessment Tool’ report to evaluate coalition capacity building efforts. | Annually | October |  |  | x
b. Review effectiveness of message dissemination | Annually | [enter date] |  |  | x
c. Will use the PBPS reports, state data, & other local reports to monitor & evaluate progress | Annually | [enter date] |  |  | x
4. Participate in statewide evaluation
a. Ensure participation in the Healthy Youth Survey | Every 2 years | In even years (2014, 2016, etc.)
b. Annual ‘Coalition Assessment Tool’ (survey) | Annually | October |  |  | x
c. Response rates for the ‘Community Survey’ | Annually | September-December |  |  | x